## Slide 1
TEAM DEEP DIVE | TECHNICAL PREPARATION
SAP ECC On-Premise
to S/4HANA on GCP
Can it be done? Every step explained. Plus: the complete data migration playbook.
PART 1
ECC On-Prem → S/4HANA on GCP: Is it Possible & How?
The answer · Prerequisites · Every step of the 6-phase journey · SUM+DMO explained · The conversion weekend
PART 2
Data Migration in Brownfield — The Complete Playbook
What data moves & how · All SAP tools side-by-side · 3rd-party tools · 8-step process your team executes · Tool selection guide

## Slide 2
PART 1 | THE DIRECT ANSWER: CAN ECC ON-PREMISE MIGRATE TO S/4HANA ON GCP?
YES
100% possible.
This is the standard path for large enterprises globally.
SAP calls it:
'System Conversion using
SUM + Database Migration
Option (DMO) to
Hyperscaler'
Under RISE with SAP, GCP Dammam
(me-central2) is the certified
destination for this exact scenario.
01
SAP's official supported path — not a workaround
SAP's SUM+DMO tool was purpose-built to take any ECC system running on-premise (on Oracle, DB2, SQL Server, or other databases) and in a single automated operation upgrade the software to S/4HANA and simultaneously migrate the database to SAP HANA on the cloud. This is SAP's primary recommended method — used in thousands of migrations worldwide.
02
ECC version matters — ECC 6.0 minimum required
The source system must be at minimum SAP ERP ECC 6.0 and it must be Unicode-enabled. Older versions like R/3 4.6 or 4.7 cannot jump directly — they require an intermediate upgrade to ECC 6.0 first (a separate 4–8 week project). The SAP Readiness Check (run in Phase 1) will confirm the source system's eligibility immediately.
03
The database does NOT need to be HANA first
A very common misconception: 'ECC must first move to HANA database before migrating to S/4HANA.' This is incorrect. SUM+DMO handles the database conversion (Oracle → HANA, DB2 → HANA, SQL Server → HANA) simultaneously with the software upgrade. One tool, one operation, one downtime window. No intermediate step required.
04
GCP KSA (Dammam) is fully SAP-certified for this
GCP's me-central2 region in Dammam runs SAP-certified M4 and C4D virtual machines listed in SAP's official HANA Hardware Directory. NCA/CCC compliance for data residency is pre-certified by SAP under RISE with SAP. This means no separate cloud security audit — SAP takes responsibility for the certification.

## Slide 3
PART 1 | PREREQUISITES — WHAT MUST BE IN PLACE BEFORE MIGRATION CAN BEGIN
Your team validates all of these during Phase 1 (Discover). Failures here become the first items in the project risk register.
SOFTWARE VERSION
✔ ECC 6.0 minimum (Enhancement Pack 0+)
Why it matters: SUM+DMO conversion scripts are built for ECC 6.0+. Older releases (R/3 4.6, 4.7) must first do an intermediate upgrade — a separate project that adds 4–8 weeks and cost before the main migration.
✔ Unicode character encoding enabled
Why it matters: S/4HANA is Unicode-only. If ECC runs in legacy non-Unicode mode (common in very old systems), a Unicode conversion is mandatory first. SAP's UCCHECK report identifies this instantly.
✔ ABAP-only stack (no dual ABAP+Java)
Why it matters: ECC systems with both ABAP and Java stacks (used for old NetWeaver Portal) cannot be converted directly. The Java components must be decommissioned or separated before SUM+DMO can run.
DATABASE & OS
✔ Any major DB is fine as source
Why it matters: SUM+DMO migrates from Oracle, IBM DB2, Microsoft SQL Server, SAP ASE (Sybase), or MaxDB. Only the source DB version matters — it must be a currently supported version. The DB itself becomes irrelevant after migration (everything moves to HANA).
✔ Supported OS on source system
Why it matters: The on-premise server running ECC must be on a supported OS version (RHEL, SLES, Windows). SUM checks this automatically in the Prerequisites Check phase. An outdated OS may require a server OS upgrade before migration starts.
GCP INFRASTRUCTURE (SAP sets up under RISE)
✔ Target GCP VMs provisioned by SAP
Why it matters: Under RISE, SAP provisions the M4/C4D high-memory VMs, Hyperdisk Extreme storage, VPC networking, HA clustering in GCP Dammam before SUM+DMO starts. This takes 3–7 days and is fully SAP's responsibility — your team just confirms readiness.
✔ Secure VPN tunnel: on-prem ↔ GCP
Why it matters: The DMOVE2S4 variant of SUM+DMO needs a secure, high-bandwidth network connection between the customer's on-premise data center and GCP Dammam so the tool can transfer data across during conversion. Bandwidth directly impacts the downtime window duration.
✔ Sufficient GCP RAM for HANA sizing
Why it matters: HANA stores the entire database in memory (RAM). If the ECC database is 3TB, the target GCP system needs at minimum 3TB RAM VMs. SAP Readiness Check calculates this exact sizing requirement — one of the most critical outputs of Phase 1.
FUNCTIONAL / BUSINESS READINESS
✔ Customer-Vendor Integration (CVI) ready
Why it matters: S/4HANA replaces separate Customer (KNA1) and Vendor (LFA1) master records with a single 'Business Partner' (BP) record. The CVI Customizing program must be activated in ECC before conversion — otherwise SUM+DMO will halt with errors on all customer/vendor records.
✔ Simplification Item Check (SICheck) passed
Why it matters: SAP's SICheck report scans ECC for configuration incompatibilities with S/4HANA — e.g., old pricing procedures, obsolete condition types, deprecated SD/MM settings. All 'errors' must be resolved before SUM+DMO will proceed. 'Warnings' are advisory.
✔ Finance: New GL activated (or migration path confirmed)
Why it matters: S/4HANA uses the Universal Journal (table ACDOCA). Systems still on 'Classic GL' must either migrate to New GL first, or a specific conversion path in SUM+DMO handles it — but this must be explicitly planned, not left as a surprise.

## Slide 4
PART 1 | THE 6-PHASE MIGRATION JOURNEY: ECC ON-PREM → S/4HANA ON GCP (SAP ACTIVATE METHODOLOGY)
1
DISCOVER
2–4 wk
WHAT HAPPENS
Business case, SAP Readiness Check, initial scan. Output: go/no-go & migration assessment report.
SAP DOES
Readiness Check · Signavio · LeanIX provided
YOUR TEAM DOES
Run Readiness Check · Fit-Gap workshops · Build business case · Confirm approach
2
PREPARE
4–6 wk
WHAT HAPPENS
Project governance, GCP environment provisioned by SAP, SUM+DMO installed on source ECC, blueprint finalised.
SAP DOES
Provisions GCP M4 VMs · Installs empty S/4HANA · Sets up Cloud ALM
YOUR TEAM DOES
Project setup · Install SUM on ECC · VPN connectivity · Config blueprint
3
EXPLORE
6–10 wk
WHAT HAPPENS
Fit-to-Standard workshops, all gaps documented, custom code remediation planned, SICheck run and resolved.
SAP DOES
Delivers SICheck report · ATC code scanner · Best Practice content
YOUR TEAM DOES
Run SICheck · Resolve all errors · ATC scan · Plan ABAP remediation
4
REALIZE
12–20 wk
WHAT HAPPENS
LONGEST PHASE: SUM+DMO conversion runs, custom code fixed, full SAP config, integrations rebuilt, all testing.
SAP DOES
Runs SUM+DMO conversion · Manages HANA infra · Provides Fiori apps
YOUR TEAM DOES
War room for conversion · Fix custom code · Full config · Data loads · UAT
5
DEPLOY
2–4 wk
WHAT HAPPENS
Final data migration, cutover playbook executed, go-live sign-off, old system decommissioned.
SAP DOES
Switches DNS · Activates prod monitoring · Scales GCP for production
YOUR TEAM DOES
Cutover playbook (200–400 tasks) · Go-live readiness sign-off
6
RUN
Ongoing
WHAT HAPPENS
Hypercare 4–8 weeks, then steady state. SAP manages infra under RISE; SI supports application.
SAP DOES
Takes over all managed ops: patching, upgrades, backups, SLA monitoring
YOUR TEAM DOES
Hypercare · Issue resolution · Knowledge transfer to customer team

## Slide 5
PART 1 | PHASE 4 DEEP DIVE — SUM+DMO: THE TECHNICAL ENGINE THAT DOES THE CONVERSION
What is SUM+DMO?
SUM = Software Update Manager (SAP's core upgrade engine) · DMO = Database Migration Option (the module that simultaneously migrates the database to HANA).
In one single automated run SUM+DMO does: (1) Upgrades the SAP software from ECC → S/4HANA · (2) Converts the database from Oracle / DB2 / SQL Server → SAP HANA · (3) Moves everything to the target GCP environment.
TWO EXECUTION MODES — CHOOSE BASED ON YOUR SCENARIO:
MODE A — DMO with System Move (Standard)
Best for: Recommended for most KSA ECC → S/4HANA on GCP migrations
HOW IT WORKS — STEP BY STEP:
1
SUM+DMO starts running on the source ECC system (still on-premise)
2
The tool performs the software upgrade and DB conversion simultaneously on the new GCP HANA target
3
Data transfers across the VPN tunnel from on-prem to GCP during the conversion run
4
Once complete, the GCP S/4HANA instance is the new production system
5
The old on-premise system is decommissioned after validation
⏱ Downtime: typically 30–80 hours during conversion weekend
⚠ Risk: Main risk: network bandwidth between on-prem and GCP. Larger DB = longer transfer.
MODE B — DMOVE2S4 (Hyperscaler-Optimised)
Best for: SAP's preferred mode when GCP is the destination — reduces downtime by 20–35%
HOW IT WORKS — STEP BY STEP:
1
SUM starts an additional application server that runs IN GCP but still belongs to the source ECC landscape
2
This GCP app server acts as a bridge — processing conversion steps distributed between on-prem and GCP
3
More work is done during 'uptime' (system still live) — reducing the actual downtime window significantly
4
The downtime-optimised conversion mode moves large tables during uptime using shadow processing
5
Final cutover is cleaner because both environments are already aligned before the switch
⏱ Downtime: 20–35% shorter than Mode A — can bring 80hr window down to ~50hrs
⚠ Risk: Slightly more complex setup. SAP's recommended method for RISE with GCP engagements.
KEY FACT: SUM+DMO is fully automated — SAP's tool, not custom scripts. Your team's role is to monitor, manage, and validate. Not to write the conversion logic.

## Slide 6
PART 1 | THE CONVERSION WEEKEND — EXACT SEQUENCE OF WHAT ACTUALLY HAPPENS
A typical Brownfield conversion weekend: Friday evening → Sunday afternoon. Total: 48–72 hours. Your team runs a 24/7 war room throughout.
TIME
EVENT
OWNER
WHAT EXACTLY HAPPENS (Step by Step)
FRI 18:00
SYSTEM FREEZE
Your Team
① All batch jobs stopped on ECC production ② Users notified: system going offline for migration weekend ③ Final backups triggered on on-premise system ④ Migration Cockpit: final master data extraction begins
FRI 20:00
SYSTEM LOCK
Your Team
① All users locked out of ECC — no more transactions ② Financial period formally closed for migration ③ Final transactional data extraction: open POs, SOs, invoices ④ Data reconciliation: extracted totals vs ECC balances confirmed
FRI 22:00
SUM+DMO STARTS
SAP Tool (Automated)
① SUM+DMO tool launched on source ECC system ② Upgrade phase begins: ECC software components updated to S/4HANA versions ③ Database schema conversion starts (Oracle/DB2 → HANA format) ④ Data begins transferring across VPN to GCP target system
SAT 06:00–
18:00
CONVERSION RUNNING
War Room Active
① SUM+DMO runs continuously — fully automated, no manual steps ② Basis team monitors progress dashboard; ready to intervene if errors occur ③ GCP temporarily scaled to maximum RAM/CPU for fastest conversion speed ④ Migration Cockpit loads final transactional data to S/4HANA in parallel
SAT 18:00
TECHNICAL VALIDATION
Your Team
① SUM+DMO completes — system is now S/4HANA on GCP HANA ② Basis team runs system health checks: all services started, no errors in logs ③ CVI check: all ECC Customers and Vendors converted to Business Partners ④ Finance: ACDOCA (Universal Journal) populated, trial balance checked cent-by-cent
SUN 08:00
BUSINESS VALIDATION
Team + Key Users
① Key users (Finance, Procurement, HR leads) log into new S/4HANA via Fiori ② Run pre-approved test scripts: create PO · post journal · run financial report ③ All critical integrations checked: live and passing data correctly ④ Project Director + Customer CIO make formal Go / No-Go decision
SUN 14:00
GO-LIVE
SAP (DNS) + Your Team
① SAP switches DNS records: all users now connect to GCP S/4HANA (not old ECC) ② Old on-premise ECC system permanently locked — read-only archive only ③ All users receive new Fiori URL and login instructions ④ Full hypercare team deployed: all hands on deck for first 48 hours

## Slide 7
PART 2
Data Migration in
Brownfield —
The Complete Playbook
Exactly how data moves · All SAP tools compared · 3rd-party options
The 8-step process your team owns · Tool selection guide
Q1
What data types must be migrated?
Q2
What SAP tools exist & how do they differ?
Q3
Are 3rd-party tools ever better?
Q4
What are the 8 steps your team executes?

## Slide 8
PART 2 | WHAT DATA NEEDS TO MIGRATE — TYPES, WHO HANDLES WHAT
In Brownfield, SUM+DMO automatically converts ~90% of all ECC data. Your team's manual migration work covers the remaining 10% — but that 10% is the most complex and highest-risk portion.
MASTER DATA
Permanent reference entities — static business objects
How handled: Mix: SUM+DMO carries most; CVI migration is manual
Business Partners (Customers & Vendors)
Method: MANUAL — CVI program
BIGGEST manual migration task in Brownfield. ECC stores customers in table KNA1 and vendors in LFA1. S/4HANA uses a single Business Partner (BP) record for both. Your team activates CVI Customising, runs the migration program, and validates every BP record. Must be done before go-live.
Material Master
Method: SUM+DMO auto
All products, raw materials, finished goods — each with up to 25 'views' (Purchasing, MRP, Accounting, Warehouse, etc.). SUM+DMO migrates all material master records automatically. Your team validates completeness post-conversion.
G/L Accounts, Cost Centres, Profit Centres
Method: SUM+DMO auto
Finance and Controlling master data. Migrated automatically by SUM+DMO. Your Finance consultant validates the hierarchy structures and chart of accounts alignment with the new Universal Journal (ACDOCA) data model.
TRANSACTIONAL DATA
Business events — documents recording actual activity
How handled: SUM+DMO handles all; team validates balances
Open Purchase Orders & Supplier Invoices
Method: SUM+DMO auto
All POs raised but not yet fully received or invoiced at cutover. Carried over by SUM+DMO. Your Procurement team validates open quantities and values match the old system line-by-line.
Open Sales Orders & Deliveries
Method: SUM+DMO auto
Active customer orders and in-progress deliveries at cutover. Customer-facing — a missed or wrong sales order means a customer doesn't receive their goods. Must be verified by your Sales/SD team.
Financial Open Items (AR/AP) & Balances
Method: SUM+DMO auto — reconcile to penny
Unpaid customer invoices (Accounts Receivable) and supplier invoices due (Accounts Payable). SUM+DMO migrates all. Your Finance team reconciles total balances against the old system before go-live sign-off. Zero tolerance for discrepancy.
CONFIG & CUSTOM OBJECTS
System settings and customer-built programs
How handled: Mix: config auto; custom code needs manual fixing
SAP IMG Configuration (all settings)
Method: SUM+DMO auto
All thousands of configuration settings in ECC — company codes, plant structures, tax codes, approval workflows, document types, pricing procedures — are carried over automatically by SUM+DMO. Your consultants validate they function correctly in S/4HANA.
Custom ABAP Programs (Z-objects)
Method: MANUAL — ABAP team fixes
Custom reports, interfaces, user exits, enhancements — code built over 15+ years. SUM+DMO copies the code but it may fail in S/4HANA because underlying DB tables changed. Your ABAP developers use ATC scanner output to identify and fix each breaking program.
Custom Z-tables & Number Ranges
Method: SUM+DMO auto — validate manually
Customer-created database tables migrate structurally via SUM+DMO but data inside them must be validated. Number ranges (which auto-number POs, invoices, etc.) must be checked post-conversion to ensure no gaps or duplicates.

## Slide 9
PART 2 | ALL SAP DATA MIGRATION TOOLS — DETAILED COMPARISON (OFFICIAL SAP TOOLS ONLY)
TOOL
WHAT IT DOES
BEST USED FOR
SKILL NEEDED
COST
LIMITATION
VERDICT
SUM+DMO
PRIMARY
Software Update Manager + Database Migration Option
SAP's core conversion engine. Automatically migrates the entire ECC database, software, configurations, transactional and historical data to S/4HANA during the conversion weekend. Handles ~90% of all data automatically.
Brownfield system conversion — always the first and primary tool. Used for both full-system conversion and DB migration.
SAP Basis consultants (specialised). Your team monitors; the tool runs itself.
Included in RISE / S/4HANA licence. No extra cost.
Migrates everything — cannot selectively exclude data. Requires a downtime window. Data quality issues in ECC are carried across as-is.
Always use first. Foundation of every Brownfield migration.
Migration Cockpit
(LTMC → 'Migrate Your
Data' app from 2021)
PRIMARY
SAP S/4HANA Migration Cockpit — replaced LSMW as official SAP migration tool
Browser-based Fiori tool with pre-built migration object templates (customers, vendors, materials, open items, etc.). Replaced the old LTMC transaction with a modern UI in S/4HANA 2021+. Also includes LTMOM (Migration Object Modeler) for custom objects.
Supplementary loads SUM+DMO doesn't fully handle: Business Partner CVI migration, initial stock loads, residual open items, custom migration objects. Two modes: File-based (CSV/Excel) or Direct Transfer (live connection to source ECC system).
Functional consultants (Finance, MM, SD) — no ABAP needed for standard objects. LTMOM requires Basis/dev for custom objects.
Included with S/4HANA licence. No additional cost.
Designed for initial data creation, not updating existing records. Complex transformations need external staging (BODS/Syniti) before loading. Not all objects have pre-built templates.
Your team's main manual migration tool alongside SUM+DMO.
SAP BODS
(Business Objects
Data Services)
SPECIALIST
SAP's enterprise ETL (Extract, Transform, Load) platform
Full ETL platform. Connects to any source system (Oracle ERP, non-SAP), applies complex transformation rules, cleanses data, and loads into S/4HANA. Supports batch and real-time processing with centralised monitoring.
Complex data transformations before loading into Migration Cockpit staging tables. Multi-source migrations. Scenarios where data must be significantly reworked before it's ready for SAP.
BODS specialist developers — more technical, higher day rates. Requires dedicated server infrastructure.
Included with SAP HANA licence (basic ETL key) but needs specialist hardware and resources.
Steep learning curve. More expensive to run than LTMC. Overkill for standard Brownfield if SUM+DMO covers most data. Requires SAP Basis to set up and maintain.
Use for complex scenarios: multi-source, heavy transformation, major data quality issues.
SLT
(SAP Landscape
Transformation)
SPECIALIST
Trigger-based real-time database replication server
Uses database triggers to capture every insert/update/delete on the source system and replicate it in real time to the target. Unlike other tools, SLT provides continuous synchronisation — not just one-time loads.
Near-zero downtime migration scenarios. Extended parallel run periods where old ECC and new S/4HANA must stay in sync for months. Phased migrations (Bluefield).
SLT specialist (Basis/technical) — rare skill, high demand, higher cost.
Separate licence required. Additional infrastructure needed.
Complex to configure and monitor. Not standard in a typical Brownfield. More relevant for Bluefield/selective scenarios or where zero downtime is a hard business requirement.
Only use when downtime window cannot exceed 2–4 hours or for extended parallel-run scenarios.
LSMW
(Legacy System
Migration Workbench)
AVOID
Original SAP migration tool built for R/2→R/3 migrations — now legacy
SAP's original file-based migration workbench. Uses BAPIs, IDocs, batch input recordings, and direct input to load data. Still present in S/4HANA on-premise but officially not SAP's recommended migration tool for S/4HANA projects.
Only valid for niche objects where no Migration Cockpit template exists and after checking SAP Note 2287723. Post-go-live minor data corrections as a last resort.
ABAP developers familiar with BAPIs and IDocs.
Included in system (legacy tool), but deprecated.
SAP explicitly does not recommend LSMW for S/4HANA. Old interfaces may have changed. No simulation capability for batch input. Cannot load hierarchical data. Very slow for large volumes. Risk of data corruption if wrong interface used.
AVOID for main migration. Check SAP Note 2287723 before any use in S/4HANA.

## Slide 10
PART 2 | THIRD-PARTY MIGRATION TOOLS — WHEN ARE THEY BETTER THAN SAP'S OWN TOOLS?
SAP's own tools handle ~95% of migrations well. Third-party tools add real value in 4 scenarios: severe data quality problems · non-SAP source systems · complex transformations · Bluefield/selective migrations.
Syniti (formerly BackOffice Associates)
Data Quality + Migration Platform
Industry-leading data quality and migration platform with direct SAP Migration Cockpit (LTMC) integration. Syniti acts as the intelligent staging layer between extraction and loading — it cleanses, deduplicates, validates, and transforms data before it reaches LTMC's staging tables.
USE WHEN:
› Customer has severe data quality issues: duplicate vendor records, missing mandatory fields, incorrect formats
› Need to extract from multiple sources simultaneously and harmonise before loading into S/4HANA
› Large migrations where automation of field mapping and validation saves hundreds of consulting hours
Verdict: Best-in-class when data quality is a major risk. Often paired with SAP Migration Cockpit for the load step.
Informatica IDMC
Enterprise ETL + Data Quality Cloud
Market leader in enterprise data integration. Connects to any source system (Oracle EBS, JD Edwards, Microsoft Dynamics, SAP ECC), applies AI-powered data quality rules, and loads into S/4HANA via BAPIs, IDocs, or direct DB connections. Cloud-native platform.
USE WHEN:
› Customer has non-SAP source systems alongside SAP ECC that must all feed into one S/4HANA
› Need ongoing data synchronisation during an extended parallel run period (months)
› Enterprise-grade data governance requirements with full audit trails and lineage
Verdict: Preferred when migration involves non-SAP sources or customer needs enterprise data governance beyond just the migration project.
SNP CrystalBridge
SAP Landscape Transformation (Bluefield Engine)
SNP invented the Bluefield approach and built CrystalBridge specifically for complex SAP landscape transformations. Can extract, transform, and selectively load SAP data — including company code splits/merges, currency conversions, and org restructuring during migration. Goes far beyond what standard SAP tools can do.
USE WHEN:
› Bluefield approach — selectively migrating data from specific company codes or legal entities only
› Mergers & Acquisitions: merging two separate SAP ECC systems into one S/4HANA
› Carve-outs: splitting one large SAP system into two separate S/4HANA instances
Verdict: The go-to tool if the migration involves org restructuring, M&A, or carve-outs. Beyond the capability of any standard SAP tool.
Precisely Automate (Winshuttle)
Excel-Based Template Loading
Excel-based data migration tooling allowing business users (not IT) to prepare data in Excel templates that are then automatically validated and loaded into SAP via BAPIs. Lower technical barrier than LTMC. Widely used for post-go-live data corrections and smaller supplementary loads.
USE WHEN:
› Smaller master data loads where business subject-matter experts (not IT) must prepare the data themselves
› Post-go-live data corrections — small, targeted updates to specific records
› Teams already comfortable with Excel wanting minimal IT dependency for data preparation
Verdict: Good for supplementary loads and post-go-live corrections. Not a primary tool for large-scale ECC Brownfield migration.

## Slide 11
PART 2 | THE DATA MIGRATION PROCESS — 8 STEPS YOUR TEAM OWNS
#
STEP
SAP'S ROLE & TOOL PROVIDED
WHAT YOUR TEAM DOES
TOOLS USED
1
SCOPE
Readiness Check provides full object inventory & data volumes
Identify every data object in scope. Classify: SUM+DMO handles automatically vs your team migrates manually. Define quality rules for each object.
SAP Readiness Check · Migration Object Modeler (LTMOM)
2
EXTRACT
SUM+DMO auto-extracts all ECC data during conversion run
For manual objects: write ABAP extraction programs or BODS jobs to pull data from ECC source tables into staging files or staging tables ready for transformation.
Custom ABAP extraction reports · SAP BODS · Direct SQL queries on ECC tables
3
PROFILE & ANALYSE
SICheck flags data-level incompatibilities. ATC flags code issues.
Profile all extracted data — find duplicates (same vendor 3 times), nulls (vendor with no bank details), format mismatches (date formats), orphan records (open PO with missing material). Document every issue found.
Syniti / Informatica data profiling · Excel pivot analysis · SAP Data Quality Management
4
CLEANSE & TRANSFORM
SAP MDG (Master Data Governance) provides cleansing workflow approvals
Fix all identified issues: deduplicate, fill mandatory fields, convert formats, map old G/L codes → new chart of accounts, convert ECC Customers+Vendors → Business Partners (CVI program). Business users must approve cleansed data.
SAP BODS · Syniti · SAP MDG · CVI Customising program · Custom ABAP transformation
5
MAP
Migration Cockpit provides field mapping templates for each migration object
Create field-by-field mapping: every source ECC field mapped to its S/4HANA equivalent. Example: ECC BSEG.DMBTR (amount) → ACDOCA.DMBTR. Value translations: old plant codes → new GCP plant codes. Approved by functional leads.
Migration Cockpit mapping editor · LTMOM for custom objects · Syniti mapping workbench
6
TEST LOADS
(3–5 cycles)
Migration Cockpit staging tables receive data and auto-validate against S/4HANA rules
Run 3–5 full test migration cycles: load data into the test S/4HANA system, review the error log, fix root causes, reload. Target: error rate below 0.5% before final production load. Each cycle improves quality.
SAP Migration Cockpit (LTMC / 'Migrate Your Data' app) · Migration error log · Custom ABAP load programs
7
VALIDATE
S/4HANA built-in reconciliation reports compare source vs target balances
Business users validate loaded data in the test system: does my vendor list look correct? Do my open POs match? Does the trial balance match to the cent? Any discrepancy is a defect that must be fixed and retested before go-live.
SAP standard reconciliation reports · Finance balance validation · Business user sign-off checklist
8
PRODUCTION LOAD
& GO-LIVE
SAP manages HANA DB performance; scales GCP infra during final load if needed
Cutover weekend: execute the final production data load using fully validated, clean data. Immediately reconcile every total. Any error goes to war room. CFO / procurement head signs off final data before DNS switch to go-live.
Migration Cockpit production run · War room monitoring dashboard · Final reconciliation sign-off checklist

## Slide 12
PART 2 | WHICH TOOL TO USE WHEN — THE QUICK DECISION REFERENCE
Use this reference card to answer any tool question in the meeting without hesitation:
IF: Converting full ECC landscape to S/4HANA?
USE: SUM+DMO
Always first — handles 90% automatically.
IF: Business Partner migration (Customer/Vendor)?
USE: CVI Program + Migration Cockpit
Activate CVI in ECC first, then load BPs via LTMC.
IF: Loading materials, open POs, G/L accounts?
USE: Migration Cockpit (LTMC)
Pre-built templates. Functional team, no ABAP.
IF: Custom ABAP code breaks post-conversion?
USE: ABAP Test Cockpit (ATC)
Run ATC scan → ABAP developers fix each issue.
IF: Severe data quality issues (duplicates, nulls)?
USE: Syniti → then Migration Cockpit
Cleanse in Syniti, load clean data via LTMC.
IF: Source includes non-SAP systems (Oracle EBS)?
USE: Informatica or SAP BODS
Extract from any source, transform, then load.
IF: Near-zero downtime (< 4hr window)?
USE: SLT + Downtime-Optimised DMO
SLT replicates live changes during conversion.
IF: Bluefield — migrating only some company codes?
USE: SNP CrystalBridge
Only tool designed for selective data transition.
IF: M&A — merging two SAP systems into one S/4HANA?
USE: SNP CrystalBridge
CrystalBridge handles complex landscape consolidation.
IF: Extended parallel run — old ECC + new S/4HANA?
USE: SLT Replication Server
Real-time sync keeps both systems aligned.
IF: Should we still use LSMW for S/4HANA?
USE: NO — use Migration Cockpit
LSMW not recommended. Check SAP Note 2287723.
IF: Small structured data load / post-go-live fixes?
USE: Migration Cockpit (File Upload)
Excel/CSV file upload mode — fast for small volumes.